**FOLPSEC RISK ASSESSMENT AND FIFTH EVALUATION REPORT**

**PROJECT MONTHS M25-M30**

**FOLPSEC RISK REGISTER**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **FOLPSEC WP** | **Potential Risk** | **Risk Assessment** | **Risk Management Assignment** | **Risk Response** |
|  All | Change in the partnership  | That risk will have negative impact on all project activities and deliverables  | WP5 leader, Steering Committee |  Not occurred |
| WP5  | Lack of consortium meetings  | That risk will have negative impact on project management and will indirectly affect the work in the other WPs | WP5 leader and project teams | More intensive cooperation and interaction via email  |
|  WP1 | Risk related to visas issuance to the Russian Federation due to changes in the application procedure  | That risk will have negative impact on the exchange scheme and will indirectly affect project implementation | WP1 leader; mobility managers | Re-scheduled secondments to IEIE SB RAS and NSU  |
| WP1 | Incoming mobility to TNEU not implemented due to the unstable situation in Ukraine | That risk will have negative impact on the exchange scheme and will indirectly affect project implementation | WP1 leader; mobility managers | Incoming mobility to TNEU transformed into outgoing one |