**FOLPSEC RISK ASSESSMENT AND THIRD EVALUATION REPORT**

**PROJECT MONTHS M13-M18**

**FOLPSEC RISK REGISTER**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **FOLPSEC WP** | **Potential Risk** | **Risk Assessment** | **Risk Management Assignment** | **Risk Response** |
| All | Change in the partnership | That risk will have negative impact on all project activities and deliverables | WP5 leader, Steering Committee | Not occurred |
| WP1 | Risk related to secondments implementation | That risk will have negative impact on all project activities in terms of content and deliverables. | WP1 leader, Project Coordinator; mobility managers | Internal consortium consultations with the assistance of the Project Officer; |
| WP2, WP3 | Risk in deliverables related to time-scale | That risk will have negative impact on FOLPSEC scientific content deployment | WP2 and WP3 leaders | Not occurred |
| WP4 | Risk related to delay in project web site development | That risk will affect the dissemination of project results and the information exchange within the consortium | WP4 leader | Use of Dropbox for internal information sharing; use of social media advantages for project results’ dissemination. |