**FOLPSEC RISK ASSESSMENT AND SECOND EVALUATION REPORT**

**PROJECT MONTHS M6-M12**

**FOLPSEC RISK REGISTER**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **FOLPSEC WP** | **Potential Risk** | **Risk Assessment** | **Risk Management Assignment** | **Risk Response** |
|  All | Change in the partnership  | That risk will have negative impact on all project activities and deliverables  | WP5 leader, Steering Committee |  Not occurred |
| WP1  | Risk related to the integration of seconded researchers  | That risk will have negative impact on the motivation of the researchers to participate in the project  | Project teams | Assistance by project teams to seconded researchers; Social program development and implementation  |
| WP1  | Risk related to secondments implementation  | That risk will have negative impact on all project activities. | WP1 leader, Project Coordinator; mobility managers | Internal consortium consultations with the assistance of the Project Officer; Revision of the Gantt chart for P1  |
| WP2, WP3 |  Risk in deliverables related to time-scale | That risk will have negative impact on FOLPSEC scientific content deployment |  WP2 and WP3 leaders |  Not occurred |
|  WP4 | Risk related to delay in project web site development  | That risk will affect the dissemination of project results and the information exchange within the consortium | WP4 leader | Use of Dropbox for internal information sharing; use of social media advantages for project results dissemination.  |